Project Planning Phase

Project Planning Template (Product Backlog, Sprint Planning, Stories, Story points)

| Date | 30TH SEPTEMBER 2026 |
| --- | --- |
| Team ID | SWTID-2026-4160 |
| Project Name | AI BlogNest API |
| Maximum Marks | 5 Marks |

Product Backlog, Sprint Schedule, and Estimation

| Sprint | Functional Requirement (Epic) | User Story No. | User Story / Task | Story Points | Priority | Team Members |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | Registration | USN-1 | As a user, I can register for the application using my email and password. | 2 | High | Team |
| Sprint-1 | Login | USN-2 | As a user, I can log into the application using my email and password. | 2 | High | Team |
| Sprint-1 | User Authentication | USN-3 | As a user, I can securely access the application after successful authentication. | 2 | High | Team |
| Sprint-2 | Blog Management | USN-4 | As a user, I can create and publish a new blog post. | 3 | High | Team |
| Sprint-2 | Blog Management | USN-5 | As a user, I can view my created and completed blog posts. | 2 | High | Team |
| Sprint-2 | Blog Management | USN-6 | As a user, I can manage my blog content through the application. | 2 | Medium | Team |
| Sprint-3 | AI Blog Generation | USN-7 | As a user, I can generate blog content using AI by providing a topic or prompt. | 3 | High | Hemapriya.S,Janani J,Jayalakshmi S,Jayasree L,Jeevana J |
| Sprint-3 | AI Blog Generation | USN-8 | As a user, I can receive AI-generated content based on the given topic. | 2 | High | Hemapriya.S,Janani J,Jayalakshmi S,Jayasree L,Jeevana J |
| Sprint-3 | AI Summarization | USN-9 | As a user, I can summarize a blog post using AI. | 2 | High | Hemapriya.S,Janani J,Jayalakshmi S,Jayasree L,Jeevana J |
| Sprint-4 | Blog Retrieval | USN-10 | As a user, I can retrieve and view my completed blogs. | 2 | High | Hemapriya.S,Janani J,Jayalakshmi S,Jayasree L,Jeevana J |
| Sprint-4 | Testing | USN-11 | As a user, I can use the major features without errors. | 2 | Medium | Hemapriya.S,Janani J,Jayalakshmi S,Jayasree L,Jeevana J |
| Sprint-4 | Final Integration | USN-12 | As a user, I can use registration, login, blog creation, AI generation, summarization, and completed blogs in one application. | 3 | High | Hemapriya.S,Janani J,Jayalakshmi S,Jayasree L,Jeevana J |

Sprint Total

Total Story Points = 27

Project Tracker, Velocity & Burndown Chart

Your template includes columns for sprint total story points, duration, start date, end date, completed story points, and actual release date.

| Sprint | Total Story Points | Duration | Sprint Start Date | Sprint End Date | Story Points Completed | Sprint Release Date |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 6 | 6 Days | 01 Oct 2026 | 06 Oct 2026 | 6 | 06 Oct 2026 |
| Sprint-2 | 7 | 6 Days | 07 Oct 2026 | 12 Oct 2026 | 7 | 12 Oct 2026 |
| Sprint-3 | 7 | 6 Days | 13 Oct 2026 | 18 Oct 2026 | 7 | 18 Oct 2026 |
| Sprint-4 | 7 | 6 Days | 19 Oct 2026 | 24 Oct 2026 | 7 | 24 Oct 2026 |

Velocity

The template explains velocity as the amount of work completed by the team during a sprint and gives an example of calculating average velocity per iteration unit.

For AI-BlogNest:

Total Story Points = 27
Number of Sprints = 4

Average Velocity = 27 ÷ 4 = 6.75 story points per sprint

Burndown Chart

A Burndown Chart represents the amount of work remaining against time and is commonly used in Agile/Scrum projects.

For your project, the planned remaining story points can be shown as:

| Sprint | Planned Remaining Points |
| --- | --- |
| Start | 27 |
| After Sprint-1 | 21 |
| After Sprint-2 | 14 |
| After Sprint-3 | 7 |
| After Sprint-4 | 0 |

https://www.visual-paradigm.com/scrum/scrum-burndown-chart/

https://www.atlassian.com/agile/tutorials/burndown-charts

Reference:

https://www.atlassian.com/agile/project-management

https://www.atlassian.com/agile/tutorials/how-to-do-scrum-with-jira-software

https://www.atlassian.com/agile/tutorials/epics

https://www.atlassian.com/agile/tutorials/sprints

https://www.atlassian.com/agile/project-management/estimation

https://www.atlassian.com/agile/tutorials/burndown-charts